GWFBT 2025

Event Planning Document

Event Overview

- Event Name: The 47th Annual Great Western Fan Belt Toss & Swap Meet

- Website: gwfbt.com

- Date: October 24- 26, 2025

- Location: DoubleTree by Hilton Golf Resort Palm Springs, Cathedral City, CA

Event Lead: Sasha Agroskina  (347)-204-0428

Coordinators:

- Registration: Sasha

- Vendors: Val Doppenberg

- Friday Dyno: Scott/Kregg (Inland Empire)

- Friday Cruise: Brad (Vintage Corsa)

- Friday Welcome Party: Sasha & Nettie (SCC)

- Car Show: Byron Linford (Utah)

- Games: Dave (Cactus) and Chuck/Nettie (SCC)

- Field Raffle: Mike Evans (San Diego)

- Gift Basket Club Competition: Sasha & Mike Evans (San Diego)

- History/Displays: Bill & Margarita (Corsa West)

- Other Activities: Val Doppenberg

- Banquet: Multi-Club

- Sunday Event: Sasha & Val

- Graphics & Merch: Scott Howey (Inland Empire)

- Advertising: Sasha

- Finances: Ronda (Vintage Corsa)

Meeting Agendas:

9/9 Zoom Meeting:

- Updates

- Review Planning Document

- Discuss Coordinators

- Gather input and ideas

9/23 Zoom Meeting:

- Updates

- Review Planning Document Changes

- Review Vendors

- Review Schedule

10/1 Meeting:

- Update on meeting with Hotel (9/30)

- Review Map

- Budget Discussion/Show Improvement ideas

- Judge Selection for car show

10/7 Meeting:

- Update on #s

- Run of Show for the Banquet

- Judge Selection for car show

10/14 Meeting:

- Update on #s

- Car Show Judges and updates

- Schedule updates

- Catering Updates/Decisions

Next Meeting 10/21 @ 5PM:

- Final Meeting!!

10/14 Update:

| Registration | 158 |
| --- | --- |
| Car Show | 71 |
| Vendor - Main | 33 |
| Vendor - Premium | 9 |
| Vendor - Indoor | 8 |
| Banquet | 184 |
| Welcome Party | 176 |
| Friday Cruise | 63 |
| Sunday Event | 30 |
| Valve Cover Race | 14 |
| Dyno | 13 |
| RV camping | 3 |
| Big Raffle | 218 |
| T-shirts | 98 |

10/7 Update: 				10/1 Update:

| Registration | 150 |  | Registration | 131 |
| --- | --- | --- | --- | --- |
| Car Show | 68 |  | Car Show | 62 |
| Vendor - Main | 31 |  | Vendor - Main | 31 |
| Vendor - Premium | 8 |  | Vendor - Premium | 8 |
| Vendor - Indoor | 8 |  | Vendor - Indoor | 8 |
| Banquet | 171 |  | Banquet | 155 |
| Welcome Party | 167 |  | Welcome Party | 155 |
| Friday Cruise | 61 |  | Friday Cruise | 58 |
| Sunday Event | 30 |  | Sunday Event | 28 |
| Valve Cover Race | 14 |  | Valve Cover Race | 13 |
| Dyno | 12 |  | Dyno | 11 |
| RV camping | 2 |  | RV camping | 2 |
| Big Raffle | 218 |  | Big Raffle | 208 |
| T-shirts | 89 |  | T-shirts | 77 |

Food

Valve Cover Races

Overflow Car Show

Map (Needs updating)

- Registration: Sasha

- Over 110 Hotel Rooms booked.  Hotel has added 20 additional rooms at a higher rate ($259 a night) – link updated on website – ends Oct 1st

- Key Dates: Prices go up: October 1st.  Banquet ticket sales ended: October 10th.

- 108 Registrations received (as of 9/23)

  - 57 Car show entrants – 16 earlies, 25 lates, 15 FCs, 1 UV

  - 130 Banquet, 129 Friday Welcome Party

- Registration bags – Hagerty bags, Summit goodies, Rally Stop, magnets (Scott), stickers (Vegas Mike), envelope with banquet ticket & Friday night & major raffle tickets & dyno ticket & valve cover car ticket, car show window card, schedule, map, t-shirt …

- For Day of Registration: Registration bags, money box and change, blank registration forms, donation container, printed map + schedule + contact phone # taped to table, table and easy-up

- Vendors: Val Doppenberg

- Registered

  - Main: 34 spaces (max: 40)

  - Premium: 9 spaces (max: 12)

  - Indoor: 8 tables (max: 15)

- Security – Parts Mike & Greg Atwood

- Vendor space layout – assigned spots

- Vendor’s with inventions – want a timeslot to present/Q&A?  Need to create Schedule for these.

- Friday Dyno: Scott/Kregg (Inland Empire)

- Friday Only: 10 AM – 5:00 PM

- Whiteboard for results

- Announcements/speaker system

- Awards at 5 PM Friday – Turbo, 2 Carb, 4 Carb, Non-Corvair.

- Friday Cruise: Brad (Vintage Corsa)

- Mapped out.  GPS total drive time: 42 minutes.

- 63 signed up

- Print route

- Start lining up at 5 PM

- Contact city for police escort/inform of cruise - no

- Photographer – Dean Mejia confirmed

- Hand out flyers Thurs/Fri for Saturday’s car show – Scott will print

- Friday Welcome Party: Sasha & Nettie (SCC)

- Catered by hotel – buffet style – food: 2 pork sliders per person + chips (150) + Hummus/Taco plates (30)

- Trivia or networking game? – Corvair Bingo – thank you Vince!

- Ticket & check in list

- Banners/decorations – Taking it back theme – fan belt toss memorabilia

- TV to display old photos and articles on FBT

- Car Show: Byron Linford (Utah)

- Staging layout/setup/park cars

- Car Show Awards – Byron will make all (Matt will provide his award).

  - People’s Choice. Ladies’ Choice.  Matt’s Choice.  Byron’s Special Awards.

  - Judge panel for main categories – 2 groups of 3 judges (1 per club) – 8 categories each + all vote for best of show (only 1 award per car)

  - 17 Categories (Best for each):

    - Early Model – Convertible, Coupe, Sedan, Wagon
Late Model – Convertible, Coupe, Sedan
Forward Control – FC Van, Rampside
Ultravan
Specialty – Survivor, Best Engineering, Best Paint, Best Patina, Best Interior, Best Water-Cooled, Best Engine, Best of Show

    - Guidelines for judging categories – Byron’s to-do

    - Byron to create order of priority of awards

    - Byron to schedule Friday judges meeting

    - Judges:

      - Vince (Central)

      - Carl (SCC)

      - Kevin Britt (Vegas)

      - Bill (Corsa West)

      - Jim (Central)

      - Doug (Utah)

- PA System – Inland Empire

- Banners – Byron will make for event and sponsors

- Supplies: Flags and string, voting ballots, ballot box, dash plaques, signage

- Max 80 - overflow in grass area by Welcome Party

- Photographer?

- Games: Dave (Cactus Club) and Nettie (SCC)

- Fan Belt Toss – SCC – Nettie (SCC)

  - setup/sign-ups/run game

  - awards -  Chuck will make 1st place team + $50 per person for 1st place

- Valve Cover Races – Chuck (SCC) and Dave (Cactus Club)

  - 14 registered

  - Youngest Racer, Oldest Racer, Best Crash, and Best Decorated Valve Cover – Cactus Club

  - 1st, 2nd, and 3rd – Chuck Rust

  - Entrance proceeds to be given to Cactus Club

- Large Jenga & cornhole (big and small) – Nettie

- Car parts Scavenger Hunt – Val

- Other: Car Puzzle/Checkers/Mancala - Sasha

- Craft table/coloring pages/hot wheels tracks/kids activities – Cactus Club (swap area) & Sasha (indoor table)

- Field Raffle: Mike Evans (San Diego)

- Simplify Drawings: 2-3 on Friday, 2-3 on Saturday, and 1 for non-claimed on Sunday

- Container for field raffle & individual ones for each Raffle Basket

- Raffle items – doing well

- Gift Basket Club Competition: Sasha and Mike Evans (San Diego)

- Proceeds will be split 50% to the winning club determined by ticket count, 50% to GWFBT

- Clubs signed up:

  - Inland Empire (Scott)

  - Vintage Corsa (Dan)

  - Cactus Club (Dave)

  - Vegas Vairs (Mike)

  - SCC (Nettie)

  - San Diego Corvair (Jim)

  - Corsa West (Margarita)

- History/Educational material: Bill & Margarita (Corsa West)

- Library in lounge area

- Display on Corvair history

- Display Fan belt toss memorabilia for Friday night

- Other activities: Val Doppenberg

- Tune-up workshop – Friday – Val & Greg Petersen

- Exhibit: Full Restoration Project car – Greg Petersen presents Tom’s car

- Exhibit: Wayne 100 corvair powered boat?

- Exhibit: Matt’s Morrvair

- Presentation & Q&A – Billet Heads – Paolo Galli

- Other Vendors present?

- Photobooth – simple setup w/ tripod, frame, hats/signs

- Nader cutout – Mike Vintage Corsa (confirmed)

- Music 2x: Car show & swap Meet – Nettie has tunes.  Paul M. has tunes.

- Banquet: Multi-Club

- Speaker scheduled to appear: Matt of Matt’s Off-Road Recovery

  - Follow up for Byron - Matt’s “Corvair” writeup

- Banquet ticket sale closed: October 10th

- Banquet tickets standby for cancellations?

- Catering – Italian Buffet

- PA system – Kregg sets up (Inland Empire)

- Centerpieces

- Awards:

  - Hard Luck Award – Chuck will make + $20 Clarks gift card

  - Longest distance in a Corvair

  - Eldest Attendee Award

  - Newest Corvair Owner (Inland Empire)

- Traditional raffle: $100 per club (Nettie presents)

- Raffle prizes: 4 buckets (Mike Evans)

  - Rebuilt Transmission

  - 2 nights Resort stay

  - Neon Corvair sign

  - TV

  - Combine all buckets for a chance at Clark’s $500 GC

- Matt might gift some Matt’s Off-road Gear

- Video recording of speech? Photographer?

- Framed corvair art/banners/etc to decorate banquet room

- Sunday Event: Sasha & Val

- Lunch at Panera Bread @12:00 PM

- Air museum @1:30pm - $20 a person for groups of 20+

- Corvairs allowed to park in the roundabout

- 30 interested registrations (about 50 people)

- Graphics & Merch: Scott (Inland)

- GWFBT T-shirts, glasses, cozies, tote bags for sale at Flatsix booth

- Advertising: Sasha

- Social media/forum posts – more engagement

- Corsa/Communique – event posted

- Advertise in Palm Springs

  - VisitPalmSprings.com & VisitGreaterPalmSprings.com

  - Hung Flyers @ local auto parts and businesses across the street.

  - Flyers to hand out at Thursday night in Palm Springs. Friday Cruise.

- Email list – sent twice.

- Facebook event – created. Share the invite!

- Keep sharing the event! And register!

- Banners for registration table

- Finances: Ronda (Vintage Corsa)

Post Show: Sasha & Scott (Inland Empire)

- Winners posted

- Post show survey

- Post show write-up – thank you and results

- Interview best of show

- Update Website and Social Media Accounts

Hotel Meeting Notes from 9/30:

- Friday Welcome Party – 6:30 cash bar/seating open 7:30 PM food 9:30 end

  - Will ask about pushing Happy Hour specials to our bar

- Banquet – 6 PM social hour/cash bar open 6:30 banquet room opens 7 PM dinner

  - plated – pot roast or chicken or vegan/vegetarian option

  - Italian Buffet

  - 10 people per table

- Car Show

  - Ramp for cars – needs to be widened by sandbags maybe

  - Sprinklers off for Thursday to Sunday

  - Power for grass area – yes - extension cord needed

  - Saturday BBQ time (11 am – 1pm or later), menu: chicken sandwiches and burgers, price: about $15

  - Setup on Thursday: Grass/parking lot/lounge area (not responsible for items)

    - No canopy’s or standing tables outside overnight due to winds

  - Seating/eating area outside - @ pool and patio

  - Overnight Parking on grass allowed from Thursday evening – there’s no lights in grass area

  - Restrictions for grass area – no glass. Personal coolers allowed. No fires.

  - Gate to grass area to be closed but not locked overnight

- General

  - Tables indoor – 15+ provided – 6ft

  - Copy of bar/restaurant menu - received

  - Check in/ out times for hotel: Check in at 4 PM.  Checkout 12 PM.

  - Bar/food hours: 11 AM to 11 PM. Breakfast at restaurant 7 AM – 11 AM.

  - Pool hours: 7 AM to 10 PM

  - Hotel Security – yes. 1 guy that makes his rounds.

  - Reviewed our Event map

  - Garbage Cans for outside – hotel will provide

  - Tables to display corvair lit

  - Restrictions for decorations – can hang on walls using removable putty

  - Coolers are allowed – no glass bottles/etc.

  - Can hang banners from our balconies – Clubs bring your banners!!

  - ATM onsite – by Bar/elevator

- V8 Club Meeting options – No charge for holding it in restaurant (empty after 11 am) – can order off the regular lunch menu (pre-order is optional)